## Slide 1: Clinic Timeline Startups

## Slide 2: Exploring
Phase I
Month 1
Month 2
Month 4
Month 3
Month 5
Month 6
Consultant travels to meet organizers, participates in Community Meeting
Environmental Scan reviewed by ECHO; determination to proceed or not
Business Plan reviewed by ECHO; determination to proceed or not
Business Plan underway
State corp. documents submitted
Board recruitment begins
Deadline for IRS document submission
Board of Directors in place
Start date: | 
Environmental Scan review date: | 
Business Plan review date: | 
Consultant Travel
Tasks with consultant assistance
Hospital Partnerships
Wellness - inspiration
Board Training - recruiting
Fundraising
Marketing and Communications
Launch Team

## Slide 3: Developing
Phase II
Board Training date: | 
Dry Run date: | 
Month 7
Month 8
Month 10
Month 9
Month 11
Month 12
Initial board training
Board meeting monthly
Explore insurance requirements
Timeline exercise
Hire Executive Director and Medical Director
Planning Team led buy Executive Director
Establish credentialing plan
Site readied
EMR training
Volunteer training
Additional staff hired
Consultant Travel
Tasks with consultant assistance
Develop job descriptions, equipment, supplies, etc.
Establish target date for clinic opening
Begin hiring process for Executive Director and Medical Director
Solidify clinic opening date
P&P manual complete
Purchase EMR
Pay insurance
Volunteer roster designed and filled with 6-week “pioneers”
Compliance
Board Training - efficacy
Human Resources
Operations
Volunteer Coordination
Facilities
Wellness – implementation
Mental Health
Launch Team

## Slide 4: Implementing
Phase III
Consultant review date: | 
Exit survey date: | 
Month 13
Month 14
Month 16
Month 15
Month 17
Month 18
Grand opening
Clinic opens
Board creates strategic plan
Dry run
Continue team building, staffing
Lab contract secured
Review clinic data
Review board function and budget
Consultant Travel
Tasks with consultant assistance
Review clinic data
Review clinic board functioning and budget
Observations and recommendations
Exit survey
Data Management
Board – strategic planning
Launch Team